## Assigned
Name of the project/system | O&M/Dev | TDL Number/Project/ TO | Vendor | Program Manager | Project Manager/Application Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT | Deployment Date | Deployed as Scheduled | Notes | Color Keys
(AAA)-AERIC | O&M | Project | Intellect Solution Inc. Rep | Lee Halbert | Kevin Phelan | Kevin Phelan | Theodore Hull | Seema Dheman | Seema Dheman | No | Yes | Not yet | No IPT was formed | N/A since its release Driven | N/A | on-going, Release driven | YELLOW = Scheduled Releases
(AAA)-AMIS ORACLE server upgrade | Dev | Project | Intellect Solutions | Lee Halbert | Brian Voohres | N/A, its ih-house development | Abdul | Seema Dheman | Seema Dheman | Yes | Yes | In Development | N/A | mm/dd/yy |  | Per email from Brian- the deliverables will be provided as needed | RED = Releases that we not released as scheduled.
AAA-AISS Oracle Database Upgrade | O&M | Project | No Vendor | Lee Halbert | Brian Voohres | N/A, its ih-house development | Theodore Hull | Seema Dheman | Seema Dheman | N/A | Yes | N/A its tech refresh | IPT was formed | mm/dd/yy |  | Meeting scehduled for Sep 29 | GREEN = Releases that were released as scheduled.
Cisco Switch Upgrade - Field Sites | O&M | Project | Accelgov | Wanda Michals | Michael Anderon | LaShemma Simmons |  | Janice Cobb | Janice Cobb |  |  | N/A its tech refresh | Yes | 2024-09-30 | SCHEDULED
Cloud Initiatives-ADAMS | Dev | N/A | MerlinOne | Wanda Michals | Falguni Jani | Kevin Phelan | Susana Raab | Janice Cobb | Janice Cobb | Yes | No | COTs product hence no Code is provided |  | 2023-11-03 | NO
DAS-: NextGen Description And Authority Service (NextGen DAS) | Dev | N/A | Satsyil | Darling Richards | Richard Steinbacher | Richard Steinbacher | Vinay Ahuja | Janice Cobb | Janice Cobb | Yes | Yes | Under Development | N/A | 2023-11-17 | NO
DAS O&M | O&M | Project | Satsyil | Darling Richards | Alex Quiroz | Kendra Guzman | Vinay Ahuja | Janice Cobb | Janice Cobb | No | Yes | Yes | N/A | N/A Release Driven | N/A | On-going, Release driven, Release date not listed in the project online
BT-Data Loss Prevention (DLP) | Dev | TO | No Vendor | Wanda Michals | Brian Voohres | N/A, its ih-house development | Akhtar Zahman | Seema Dheman | Seema Dheman | Yes | N/A | Under Development | N/A | mm/dd/yy |  | Sent On 04/18/24
ECRM-Electoral College Tracking Tool (ECT) | Dev | Project | in-House Dev | Senthil Kumar Sadasivam | Kenyetta Haywood | N/A, its ih-house development | Frank Reed | Seema Dheman | Seema Dheman | Yes | Maybe | Under Development | N/A | mm/dd/yy |  | Sent On 04/18/24
PACS-ePACS (A1) | Dev | N/A | Communications Resource Incorporated (CRI) | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton and Debra Anderson | Janice Cobb | Janice Cobb | Yes | No | COTs product hence no Code is provided | N/A | 2023-03-31 | NO | Project is technically delayed to COVID19 but ongoing.
PACS-ePACS (A2) | Dev | N/A | Communications Resource Incorporated (CRI) | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided | N/A | 2022-11-15 | NO
PACS-ePACS (Atlanta) | Dev | N/A | Convergint | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-06-10 | NO | Separate tab on the e-PACS CIL
PACS-ePACS (Lenexa) | Dev | N/A | TBD | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-05-10 | NO | Separate tab on the e-PACS CIL
PACS-ePACS (LBJ) | Dev | N/A | Stanley | Wanda Michals | Joseph Adekunle | Rama Ganti | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-01-09 | NO
PACS-ePACS (Suitland) | Dev |  | Convergint | Wanda Michals | Joseph Adekunle | Rama Ganti | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-06-30 | NO | Separate tab on the e-PACS CIL
PACS-ePACS-(Eisenhower) | Dev |  | TBD | Wanda Michals | Joseph Adekunle | Rama Ganti | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  |  |  | /
ECRM-Knowledge Management(Case Reference Guide) | Dev | TO | N/A In-House Dev | Senthil Sadasivam | Kenyetta Haywood | N/A no contract support | Frank Reed | Seema Dheman | Seema Dheman | Yes | May be | Under Development | Not Known | 2024-05-31 | SCHEDULED | Sent On 04/18/24
ECRM-Cloud Initiatives | O&M | N/A | In house development | Darling Richards | Bobby Goddard | Frank Samuels | Bobby Goddard | Seema Dheman | Seema Dheman | No | Release Driven | N/A its a SaaS product | N/A | NOT LISTED |  | not listed in project online
E-DOCS (currently known as FRPS) | O&M | N/A | TBD | Senthil Sadasivam | Maurice Mitchell | Maurice Mitchell | Maurice Mitchell | Janice Cobb | Janice Cobb | N/A | Release Driven | Yes | N/A | N/A Release Driven | N/A | 4/15/24 - Upcoming project. Sole source selection for RFQ in May-2024.
EOP-45 | Dev | N/A | Sapient | Lee Halbert | Kenneth Morrison | Kenneth Morrison | Kevin Liu | Seema Dheman | Seema Dheman | NO | If applicable | Part of ERA O&M | N/A | 2024-04-01 | YES | NO CIL report will be publsihed, refer to CIL Report NOTE EOP-45 Text Release (RFC-30926) will commence 04/01 thru 04/02.
EOP O&M | O&M | N/A | IBM | David Lake | Sridhar Karegowdra | Naiger Chambers | Sridhar Karegowdra | Seema Dheman | Seema Dheman | No | Yes | Under Development | N/A | N/A Release Driven | N/A | Release driven
ERA O&M (Base) | O&M | N/A | IBM | David Lake | Jesssica Bland | Nagier Chambers | Mike Haines | Janice Cobb | Janice Cobb | No | Yes | Yes | N/A | N/A Release Driven | N/A
ERA2.0 - O&M | Dev | N/A | Sapient | David Lake | Jessica Bland | Jay Hanchey | Kevin McCarthy | Seema Dheman | Seema Dheman | No | Yes | Release Driven | N/A | N/A Release Driven | N/A | It will be deployed around Jan 14 with Base Migration Code base. 01/14/22 for cycle k release 04/15/24: RFC-30935 (ERA_24.1.2.0(FB)_FY-24_07)
electronic Records Management Application (eRMA) | Dev | N/A |  | Darling Richards |  |  |  | Seema Dheman | Seema Dheman | [6 empty] | Followed up with PM on 01/29/24
NDC-ADDRESS URTS/STAIRS-HighView O&M | O&M | N/A | CACI | Senthil Sadasivam | Thanh-Nhi (Nhi) Vo | Frank Samuels | Thanh-Nhi (Nhi) Vo | Janice Cobb | Janice Cobb | No | Yes | Yes, Release Driven
Cloud Initiatives-MCMD O&M (PaaS) | O&M | Project | Gallery Systems | Lee Halbert | Sekar Kapa | Kim Koons | Kim Koons | Janice Cobb | Janice Cobb | NO | Yes | NO | No IPT was formed | N/A Release Driven | N/A | O&M Project, CM Plan wil be completed in OCt 2020 No current updates at this time
NAC O&M | O&M | N/A | SatSyil | Darling Richards | Alexander Quiroz | Kendra Guzman | Vinay Ahuja | Seema Dheman | Seema Dheman | No | Yes | Yes | N/A | N/A Release Driven | N/A | on-going, Release driven.not listed in project online
BT-NARA Infrastructure | O&M | N/A | Accel.gov | Wanda Michals | N/A | LaSheema Simmons | Rick Lopez | Janice Cobb | Janice Cobb | Yes | N/A | N/A | No | N/A Release Driven | N/A
NDC-ADRRESS Project ( Un Classified) | O&M | N/A | CACI | Carol Harris | Than-Nhi (Nhi) Vo | Kevin Phelan | Than-Nhi (Nhi) Vo | Janice Cobb | Janice Cobb | N/A | Yes | NO | N/A | not listed in project online |  | on-going, Release driven
NDC-URTS Project (Un Classified) | O&M | N/A | CACI | Carol Harris | Than-Nhi (Nhi) Vo | Kevin Phelan | Than-Nhi (Nhi) Vo | Janice Cobb | Janice Cobb | N/A | N/A | NO | N/A | not listed in project online |  | on-going, Release driven
NISP Siebel App-RCPBS | O&M | N/A | Optimos | Lee Halbert | Joseph Adekunle | Timothy Rhodes | Dharma Reddy | Seema Dheman | Seema Dheman | N/A | N/A (COTS) | N/A | No IPT was formed | 2021-11-05 | NO | on-going, Release driven
BT-NPRC LAN | Dev | N/A | KDS | Wanda Michals | Michael Anderson | LaSheema Simmons | Garmani Maw | Janice Cobb | Janice Cobb | Yes | N/A | N/A | Not Known | 2023-08-18 | NO | This is an Infrastructure project on Prem.
Perfomance Management and Reporting System (PMRS) | O&M | PWS | ASRC Federal | Senthil Sadasivam | ThanNhi Vo | Maurice Mitchell | Alex Honch | Seema Dheman | Seema Dheman | No | Yes | No | Not Known | mm/dd/yy |  | NO CIL Report needed, Refer to descripion in the PVCS VM for thje CIL Report
Social Media Archiving Tool | Dev | N/A | N/A Innovation | Darling Richards | Falguni Jani | N/A no contract support | Carol Lagundo | Seema Dheman | Seema Dheman | No | N/A Its a SaaS project | N/A it a COTs product | N/A | mm/dd/yy
Visitor Service System (VSS) | O&M | N/A | N/A | Lee Halbert | Alexander Quiroz | Carol Harris | Ken Bostic (Acme) | Seema Dheman | Seema Dheman | No, its Release driven | N/A Its a SaaS project | N/A it a COTs product | N/A | mm/dd/yy |  | Not listed in project online
WTC_Ford Library Website Redesign | Dev | N/A | Agileana | Darling Richards | Sharmaine Anderson | James Mischke | James Mischke | janice Cobb | janice Cobb | Yes | N/A. Its a COTs product |  |  | mm/dd/yy |  | Seema reviewd and provided comments on the TP
WTC_National Archives Museum Website Redesign | O&M | N/A | Agileana | Darling Richards | Brian Voorhees | James Mischke | James Mischke | Janice Cobb | Janice Cobb | Yes |  |  | Yes | mm/dd/yy
History Hub Live Chat Enhancement |  |  |  | Darling Richards | Bobby Goddard |  |  | Janice Cobb | Janice Cobb |  | N/A it's a SaaS product | There is no custom code | Yes | mm/dd/yy |  | Pam Wright is the System Owner
A2 Data Modernization |  |  |  | Wanda Michals |  |  |  | Janice Cobb | Janice Cobb |  |  |  |  | mm/dd/yy
mm/dd/yy
Upcoming Projects
Upcoming Projects | [15 empty] | Up
IPv6 Implementation | [7 empty] | TBD | TBD |  |  |  |  | 2023-05-26 | NO
Project Online (Refer to Notes) Per convo with Tamika this is part of Office 365 | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Per PRB on 03/02/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed.
Share Point (Refer to Notes)Per convo with Tamika this is part of Office 365 | [7 empty] | Seema Dheman | Seema Dheman |  |  |  |  | 2023-05-09 | NO | Per PRB on 03/02/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed.
DCU Server Upgrade | O&M | [6 empty] | Janice Cobb | Janice Cobb |  |  |  |  | 2023-08-31 | NO | Per PRB on 03/16/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed. Email sent to LaShemma on 03/16/22.
RCPBS Upgrade | [7 empty] | TBD | TBD |  |  |  |  | 2022-04-12 | NO | Per PRB on 03/16/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed. Email sent to LaShemma on 03/16/22.
Trump Library Enhancements Updates |  |  |  |  | Brian Voorhees |  |  | TBD | TBD |  |  |  |  | mm/dd/yy |  | First email sent on 07/27/22 and 2nd email sent on 08/03/22 7/25/23 - Not in Project Online.
NARA EEO Tracking System | Dev | N/A |  | Joseph Gryder | Kenyetta Haywood | Maurice Mitchell |  | Janice Cobb | Janice Cobb | Yes | N/A its a COTS-SaaS product | No, there is no custom code | Yes | mm/dd/yy |  | IQ/Test (Chandni) wb in a monitoring role. 7/25/23 - The TP is still in draft. Seema provided comments to TP on 11/20/23
MiDAS Search and Access Portal | [7 empty] | TBD | TBD |  |  |  |  | mm/dd/yy |  | Yes
Agency and Related Services/ERA 2.0 |  |  |  |  | Jessica Bland |  |  | Seema Dheman | Seema Dheman |  |  |  |  | mm/dd/yy |  | Seema reviewed the TP and provided comments
NAC-Artificial Intelligence - Semantic Search Pilot | [7 empty] | Seema Dheman | Seema Dheman |  |  |  |  | mm/dd/yy
AAA-AISS Oracle Database upgrade |  |  |  | Senthil Kumar Sadasivam | Kenyetta Haywood |  |  | Seema Dheman | Seema Dheman |  |  |  |  | 2023-09-20 | NO | NO CM checklist or deliverables will be provided, List Refer to Email
Incorporation By Reference (IBR) | [7 empty] | Seema Dheman | Seema Dheman |  |  |  |  | mm/dd/yy |  | Sherli added to IPT on 07/11/23.Provided comments on the draft TP on 09/06/23
Artificial Intelligence Machine Learning (AI_ML) | [7 empty] | Janice Cobb | Janice Cobb
Catalog UX Improvements – Phase 2 (AAD Release 1) | Dev | [6 empty] | Seema Dheman | Seema Dheman | [6 empty] | Sherli made me the IPT member from CM side
Records Schedule & Disposition Policy Tool (RSDPT) |  |  |  | Darling Richards | Kenyetta Haywood |  |  | Janice Cobb | Janice Cobb |  |  |  | Yes | 2024-12-31 | SCHEDULED
PII Data Detection T&E | [7 empty] | Seema Dheman | Seema Dheman |  |  |  | Yes |  |  | Testing: Farooq Khan, Systems Engineering: Swapna Challa, Security: David Omorogbe.
Digital Presidential Library Portals to the Catalog | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Became part of IPT on 03/18/24
NextGen Finding Aids | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Became part of IPT on 03/18/25
Archives.gov Redesign | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Became part of IPT on 03/18/26
Switch Upgrade - Field Sites |  |  |  | Wanda Michals | Michael Anderson/ David Orlovitz |  |  | Janice Cobb | Janice Cobb
[8 empty] | Total Count for CM Lead | Total Count for CM Analyst
[7 empty] | Seema Dheman | 23 | 23
[7 empty] | Janice Cobb | 28 | 28
[7 empty] | Total Number of Projects | 55 | 55
[7 empty] | Projects Needing CM Lead or CM Analyst | 4 | 4
Note on A54: Per Convo with TamikaTamika Ellis, Sep 1, 2021, 9:10 AM SharePoint and Project online are sort of under O365 we just put them as separate projects because they will go out after the O365 roll out. -Seema Dheman
Note on Q58: Per Richard's email Richard Steinbacher Oct 18, 2022, 2:05 PM (1 day ago) to me, Kendra Hi Seema, We will definitely provide this to you after it's finalized. Thank you, Richard On Tue, Oct 18, 2022 at 1:23 PM Seema Dheman <seema.dheman@nara.gov> wrote: Hi Richard, Please let me know whenever the TP is finalized so I can go over the CM checklist with you. Thanks On Wed, Oct 5, 2022 at 2:39 PM Richard Steinbacher <richard.steinbacher@nara.gov> wrote: Thank you Seema! -Seema Dheman

## Completed FY 22
Note on P17: Per richard's email on 01/27/22 DAS ORACLE Replacement Inbox Richard Steinbacher 7:51 AM (35 minutes ago) to me Yes, please close this out. Thanks Seema. On Thu, Jan 27, 2022 at 7:44 AM Seema Dheman <seema.dheman@nara.gov> wrote: Great, Then I can remove it from the CM support list. Thanks for the quick response. On Thu, Jan 27, 2022 at 7:41 AM Richard Steinbacher <richard.steinbacher@nara.gov> wrote: Hi Seema, This project is actually OBE as it is part of the NextGen DAS project. Thank you, Richard On Thu, Jan 27, 2022 at 7:32 AM Seema Dheman <seema.dheman@nara.gov> wrote: Hi Richard, Per our earlier conversation this project is on Hold. Please let me know if the management decides to restart this project. I will not follow up on this one now. Thanks -Seema Dheman

## Completed FY 18
Note on L21: Per Sam Lee email on 12/03/18 Clean up share drive Inbox x Samuel Lee 12:52 PM (2 minutes ago) to me, David Yes, I agree. Thanks. On Mon, Dec 3, 2018 at 12:44 PM Seema Dheman <seema.dheman@nara.gov> wrote: Sam, Since its transformed it into Google Team Drive now so from CM perspective its closed. Please let me know if you disagree. thanks On Mon, Dec 3, 2018 at 12:39 PM Samuel Lee <Samuel.Lee@nara.gov> wrote: I think this effort morphed into the Share Drive Migration. The original plan was to migrate files into Microsoft shares, but the target is Google Team drive now. Thanks. On Mon, Dec 3, 2018 at 10:47 AM Seema Dheman <seema.dheman@nara.gov> wrote: Hi Sam, Is the Clean up share Drive project completed? Please let me know. Thanks -Seema Dheman

## Completed FY16
Total Number of Projects Closed in FY16:
0

## CM Only Activities
In-Progress
Not Started
Completed

## On_Hold Status
TDL Number | Project Name | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Notes
| Researcher Registration System (RRS) |  | Ira H. |  |  | Seema Dheman | Seema Dheman |  |  |  | Per Ira's email on 09/09/15-RRS is on hold status on this time since source selection was cancelled. (ip)
| e-VETS RECS 2.0 |  | Joe |  |  | Seema Dheman | Seema Dheman |  |  |  | Project on hold. It will subsumed by CMRS. NO CM suppot required at this time Email sent to Joe Falcione on 04/22/16 (ip)
| Audits and Assurance II-P | N/A | Deborah Steel | Mamta Rai |  | Seema Dheman | Seema Dheman | N/A | N/A |  | Documentation only. On Hold
| CCTV |  | Wanda Michals | Delray Wiley |  | David Talon | David Talon | Yes | N/A | N/A | Per IPJ-RPRT-Project_Status ...Awatiting Funding, On Hold
| Document Utility Conversion (DCU) |  |  | Delray Wiley |  | David Talon | David Talon | No |  | N/A | David became CM Lead starting Jan 6, 2017. Per the IPJ-RPRT-Project_Status-20170530 its in deferred status
| ePMS |  |  | Kevin Phelan |  | David Talon | David Talon |  |  | David Talon | Per IPJ-RPRT-Project on 05/30/17_Status ...Awatiting Funding, On Hold.
Digitization Lab Hitachi SAN Replacement |  | Not known at this time | Wanda Michals | Kevin Phelan | Do not know yet | Seema Dheman | Seema Dheman | Yes |  |  | Project on hold for pending the sign-off of a NARA-approved baseline for Windows Server 2016
Virtulization Project | [10 empty] | Samuel Lee 10:27 AM (29 minutes ago) to Thomas, me I do not recall this project, either. No PM assignment is available. On Mon, May 20, 2019 at 9:44 AM Thomas Mcandrew <Thomas.McAndrew@nara.gov> wrote: Seema, I am not familiar with this project? Is this an Ops project? Thanks, Tom M
| SCTS Security Clearance Tracking | MicroPact | Ira Harley | Deb Anderson | Jeff Monroe | David Talon | David Talon | Yes | No | no ipt | This has been extened one year to allow for a new PWS- 0n hold
Total Number of Closed Projects:
7

## References
•Technology Refresh: IT Investments that consist of a hardware or software technology refresh that do not significantly change existing business processes. The minimum dollar threshold is $1 and there is no maximum dollar threshold. •Small: IT Investments with Development Modernization and Enhancement (DME) costs between $1 and $1 million (M) OR annual Operations and Maintenance (O&M) (i.e., steady state) costs between $1 and $500 thousand (K). •Medium: IT Investments with DME costs between $1M and $10M OR annual O&M (steady state) costs between $500K and $1M. •Large: IT Investments with costs of at least $10M OR annual O&M (i.e., steady state) costs of at least $1M. Financial management systems or investments that are deemed by the CIO to be mission-critical to NARA also fall into this threshold.

## CM Support not Req
Project Name | TDL Number | Vendor | Program Manager | Project Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code exists in CM | IPT Lead | Notes
Enterprise Asset Management (EAM) |  |  | Ira Harley |  |  |  | Seema Dheman | Seema Dheman | N/A |  |  |  | NO CM support is required at this time. Ira infromed informally to Seema
Case Management |  |  | Darling Richards |  | Marlon Andrews |  | Seema Dheman | Seema Dheman |  |  |  |  | CM support is not required at this time. Per Marlon's email on 06/15/17: CM Support is not required at this time since we have only acquired licenses. We are doing phase two to get an integrator and when that is awarded (September) than we will need CM.
Infrastructure A2 Cabling |  |  | Wanda Michals | Bill Day |  |  |  |  | No |  |  |  | Per conversation with Bill Day no contract support required for A2 Cabling
1940 Census Redesign |  |  |  | Falguni Jani |  |  | David Talon | David Talon |  |  |  |  | On Hold
PDMT (Jira Tool) | N/A | TBD | Darling Richards | Falguni Jani | TBD | Andrew Wilson | David Talon | David Talon | NO | No | N/A | No IPT was formed | These requirements were moved to 1950 Census.

## Completed
TDL Number | Project Name | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Notes
TDL_01_13_AAD_0009 | AAD Development/Test Site Implementation Plan | Deb Steel | Frank Samuels | Development | 2013-07-29 | Carol Harris | Seema Dheman
TDL_02_14_TEC_0003 | Cloud Development and Test |  |  |  | Unk | Unk | Kim Scates
TDL_00_12_TEC_0004 | Consolidate and Refresh the NetApp Infrastructure | Amy Anderson |  | Documentation | 2012-09-25 | Carol Harris | Seema Dheman
FY13-ITAS-PM-TDL-003 | Digital Processing Environment (DPE) | David Lake | Frank Samuels | Documentation | 2013-10-24 | Seema Dheman | Kim Scates
TDL _00_12_BAS_0001-1 | Download of Search Results |  |  | Development | 2012-05-11 | N/A | Seema Dheman
ITAS-PM-TDL-003 | Electronic Performance Management System | Jim Mischke | Jim Mischke | Development | 2013-10-28 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enhancement of NARA Web Filtering (EWF) | Laima Kuring | Laima Kuring | Documentation | 2013-11-26 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Asset Management(EAM) | Ira Harley | Ira Harley | Documentation | 2013-10-22 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Backup (EB) | Queenie Ogden | Queenie Ogden | Documentation | 2014-01-24 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Cloud Strategy (ECS) | Frank Samuels | Frank Samuels | Documentation | 2013-12-18 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Identity Management / HSPD-12 Concept (EIM) | William Day | William Day | Documentation | 2013-11-14 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Storage Management (ESM) | Queenie Ogden | Queenie Ogden | Documentation | 2014-01-24 | Seema Dheman | Seema Dheman
EOP Data Migration | EOP Data Migration | Ken Hawkins | Tom McAndrew | Development |  | Carol Harris
EOP Upgrade | EOP Small Tasks | Ken Hawkins | Tom McAndrew | Development |  | Carol Harris | Kim Scates
TDL_01_13_EOP_0005 | EOP Small Tasks |  |  | IBM | Ken Hawkins
TDL_02_14_BAS_0011 | ERA Base Browser Compatibility | David Lake | Frank Samuels | Development | 2013-09-27 | Carol Harris | Seema Dheman
TDL_00_12_BAS_0001-2 | ERA Base Performance Analysis | David Lake | Frank Samuels | Documentation | 2012-06-18 | N/A | Kim Scates
TDL_01_13_BAS_0001-3 | ERA Base Search Performance |  |  | IBM
TDL_00_12_TEC_0003 | ERA Development and Test in IBM Smart Cloud | Dyung Le |  | Development | 2012-09-25 | Carol Harris | Kim Scates
| FOIA Functionality | med | 1 | VION | Ken Hawkins
FY13-ITAS-PM-TDL-001 | Google Gaps |  |  | Development |  | Seema Dheman | Seema Dheman
Cellular Repeater |  | 1 | Biil D.
TDL_X.X | OCAR | med | 1
TDL_00_12_OPA_0002 | Online Public Access (OPA) Instance of ERA | Richard Steinbacher |  | Development | 2012-08-15 | Carol Harris | Kim Scates
Project ID | Project Name | Program Manager | Project Manager | Project Type | Baseline Start | CM Project Lead | CM Project Analyst
TDL_01_13_OPA_0008 | Public Access to EOP43 via OPA | Richard Steinbacher | Dorothy Fields | Development | 2013-07-15 | Carol Harris | Seema Dheman
ITAS-PM-TDL-005 | Researcher Registration |  | Ira Harley | Documentation | 2013-09-27 | Seema Dheman | Seema Dheman
Unified Communications (UC) | SAIC |  |  | Documentation | 2013-12-30 | Seema Dheman | Seema Dheman
TDL_01_13_TEC_0006 | SE Base Small Fixes | Dyung Le | Frank Samuels | Development | 2013-09-30 | Carol Harris | Seema Dheman
TDL_02_13_SEC_0010 | Security Fixes | Ben McElyea | Amy Anderson | Development | 2013-09-30 | Carol Harris | Seema Dheman
TDL_01_13_TEC_0007 | Tech Refresh part II | Amy Anderson | Amy Anderson | Development | 2013-07-23 | Carol Harris | Seema Dheman
ITAS-PM TDL-0001 | Websites to the Cloud (WTC) | Theodore Dryer | Theodore Dryer | Documentation | 2013-11-13 | Seema Dheman | Seema Dheman
| Mobile Device Management |  |  |  |  | Janice Cobb
N/A | SIP |  |  |  |  | Seema Dheman | Elena Donskaia |  |  |  | Project has been completed.
| Web Server Refresh |  |  |  |  | Seema Dheman | Seema Dheman |  |  |  | No CM support required as per IT Projects meeting on 11/19/15 (G)
N/A | Digital Signage |  | Alex Turrel | Vera Williams |  | Seema Dheman |  |  |  |  | No CM support required. Project closed. Email checked into PVCS
| Website to Cloud (WTC) | Viderity | Wanda Michals | Vera Williams | Brian Connor | Janice Cobb | Janice Cobb | No | No |  | Cloud hosting.
Total Number of Closed Projects:
35