## Assigned
Name of the project/system | O&M/Dev | TDL Number/Project/ TO | Vendor | Program Manager | Project Manager/Application Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT | Deployment Date | Deployed as Scheduled | Notes | Color Keys
(AAA)-AERIC | O&M | Project | Intellect Solution Inc. Rep | Lee Halbert | Kevin Phelan | Kevin Phelan | Theodore Hull | Seema Dheman | Seema Dheman | No | Yes | Not yet | No IPT was formed | N/A since its release Driven | N/A | on-going, Release driven | YELLOW = Scheduled Releases
(AAA)-AMIS ORACLE server upgrade | Dev | Project | Intellect Solutions | Lee Halbert | Brian Voohres | N/A, its ih-house development | Abdul | Seema Dheman | Seema Dheman | Yes | Yes | In Development | N/A | mm/dd/yy |  | Per email from Brian- the deliverables will be provided as needed | RED = Releases that we not released as scheduled.
AAA-AISS Oracle Database Upgrade | O&M | Project | No Vendor | Lee Halbert | Brian Voohres | N/A, its ih-house development | Theodore Hull | Seema Dheman | Seema Dheman | N/A | Yes | N/A its tech refresh | IPT was formed | mm/dd/yy |  | Meeting scehduled for Sep 29 | GREEN = Releases that were released as scheduled.
Cisco Switch Upgrade - Field Sites | O&M | Project | Accelgov | Wanda Michals | Michael Anderon | LaShemma Simmons |  | Janice Cobb | Janice Cobb |  |  | N/A its tech refresh | Yes | 2024-09-30 | SCHEDULED
Cloud Initiatives-ADAMS | Dev | N/A | MerlinOne | Wanda Michals | Falguni Jani | Kevin Phelan | Susana Raab | Janice Cobb | Janice Cobb | Yes | No | COTs product hence no Code is provided |  | 2023-11-03 | NO
DAS-: NextGen Description And Authority Service (NextGen DAS) | Dev | N/A | Satsyil | Darling Richards | Richard Steinbacher | Richard Steinbacher | Vinay Ahuja | Janice Cobb | Janice Cobb | Yes | Yes | Under Development | N/A | 2023-11-17 | NO
DAS O&M | O&M | Project | Satsyil | Darling Richards | Alex Quiroz | Kendra Guzman | Vinay Ahuja | Janice Cobb | Janice Cobb | No | Yes | Yes | N/A | N/A Release Driven | N/A | On-going, Release driven, Release date not listed in the project online
BT-Data Loss Prevention (DLP) | Dev | TO | No Vendor | Wanda Michals | Brian Voohres | N/A, its ih-house development | Akhtar Zahman | Seema Dheman | Seema Dheman | Yes | N/A | Under Development | N/A | mm/dd/yy |  | Sent On 04/18/24
ECRM-Electoral College Tracking Tool (ECT) | Dev | Project | in-House Dev | Senthil Kumar Sadasivam | Kenyetta Haywood | N/A, its ih-house development | Frank Reed | Seema Dheman | Seema Dheman | Yes | Maybe | Under Development | N/A | mm/dd/yy |  | Sent On 04/18/24
PACS-ePACS (A1) | Dev | N/A | Communications Resource Incorporated (CRI) | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton and Debra Anderson | Janice Cobb | Janice Cobb | Yes | No | COTs product hence no Code is provided | N/A | 2023-03-31 | NO | Project is technically delayed to COVID19 but ongoing.
PACS-ePACS (A2) | Dev | N/A | Communications Resource Incorporated (CRI) | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided | N/A | 2022-11-15 | NO
PACS-ePACS (Atlanta) | Dev | N/A | Convergint | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-06-10 | NO | Separate tab on the e-PACS CIL
PACS-ePACS (Lenexa) | Dev | N/A | TBD | Wanda Michals | Joseph Adekunle | Jim Morton | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-05-10 | NO | Separate tab on the e-PACS CIL
PACS-ePACS (LBJ) | Dev | N/A | Stanley | Wanda Michals | Joseph Adekunle | Rama Ganti | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-01-09 | NO
PACS-ePACS (Suitland) | Dev |  | Convergint | Wanda Michals | Joseph Adekunle | Rama Ganti | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  | 2023-06-30 | NO | Separate tab on the e-PACS CIL
PACS-ePACS-(Eisenhower) | Dev |  | TBD | Wanda Michals | Joseph Adekunle | Rama Ganti | Jim Morton | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | COTs product hence no Code is provided |  |  |  | /
ECRM-Knowledge Management(Case Reference Guide) | Dev | TO | N/A In-House Dev | Senthil Sadasivam | Kenyetta Haywood | N/A no contract support | Frank Reed | Seema Dheman | Seema Dheman | Yes | May be | Under Development | Not Known | 2024-05-31 | SCHEDULED | Sent On 04/18/24
ECRM-Cloud Initiatives | O&M | N/A | In house development | Darling Richards | Bobby Goddard | Frank Samuels | Bobby Goddard | Seema Dheman | Seema Dheman | No | Release Driven | N/A its a SaaS product | N/A | NOT LISTED |  | not listed in project online
E-DOCS (currently known as FRPS) | O&M | N/A | TBD | Senthil Sadasivam | Maurice Mitchell | Maurice Mitchell | Maurice Mitchell | Janice Cobb | Janice Cobb | N/A | Release Driven | Yes | N/A | N/A Release Driven | N/A | 4/15/24 - Upcoming project. Sole source selection for RFQ in May-2024.
EOP-45 | Dev | N/A | Sapient | Lee Halbert | Kenneth Morrison | Kenneth Morrison | Kevin Liu | Seema Dheman | Seema Dheman | NO | If applicable | Part of ERA O&M | N/A | 2024-04-01 | YES | NO CIL report will be publsihed, refer to CIL Report NOTE EOP-45 Text Release (RFC-30926) will commence 04/01 thru 04/02.
EOP O&M | O&M | N/A | IBM | David Lake | Sridhar Karegowdra | Naiger Chambers | Sridhar Karegowdra | Seema Dheman | Seema Dheman | No | Yes | Under Development | N/A | N/A Release Driven | N/A | Release driven
ERA O&M (Base) | O&M | N/A | IBM | David Lake | Jesssica Bland | Nagier Chambers | Mike Haines | Janice Cobb | Janice Cobb | No | Yes | Yes | N/A | N/A Release Driven | N/A
ERA2.0 - O&M | Dev | N/A | Sapient | David Lake | Jessica Bland | Jay Hanchey | Kevin McCarthy | Seema Dheman | Seema Dheman | No | Yes | Release Driven | N/A | N/A Release Driven | N/A | It will be deployed around Jan 14 with Base Migration Code base. 01/14/22 for cycle k release 04/15/24: RFC-30935 (ERA_24.1.2.0(FB)_FY-24_07)
electronic Records Management Application (eRMA) | Dev | N/A |  | Darling Richards |  |  |  | Seema Dheman | Seema Dheman | [6 empty] | Followed up with PM on 01/29/24
NDC-ADDRESS URTS/STAIRS-HighView O&M | O&M | N/A | CACI | Senthil Sadasivam | Thanh-Nhi (Nhi) Vo | Frank Samuels | Thanh-Nhi (Nhi) Vo | Janice Cobb | Janice Cobb | No | Yes | Yes, Release Driven
Cloud Initiatives-MCMD O&M (PaaS) | O&M | Project | Gallery Systems | Lee Halbert | Sekar Kapa | Kim Koons | Kim Koons | Janice Cobb | Janice Cobb | NO | Yes | NO | No IPT was formed | N/A Release Driven | N/A | O&M Project, CM Plan wil be completed in OCt 2020 No current updates at this time
NAC O&M | O&M | N/A | SatSyil | Darling Richards | Alexander Quiroz | Kendra Guzman | Vinay Ahuja | Seema Dheman | Seema Dheman | No | Yes | Yes | N/A | N/A Release Driven | N/A | on-going, Release driven.not listed in project online
BT-NARA Infrastructure | O&M | N/A | Accel.gov | Wanda Michals | N/A | LaSheema Simmons | Rick Lopez | Janice Cobb | Janice Cobb | Yes | N/A | N/A | No | N/A Release Driven | N/A
NDC-ADRRESS Project ( Un Classified) | O&M | N/A | CACI | Carol Harris | Than-Nhi (Nhi) Vo | Kevin Phelan | Than-Nhi (Nhi) Vo | Janice Cobb | Janice Cobb | N/A | Yes | NO | N/A | not listed in project online |  | on-going, Release driven
NDC-URTS Project (Un Classified) | O&M | N/A | CACI | Carol Harris | Than-Nhi (Nhi) Vo | Kevin Phelan | Than-Nhi (Nhi) Vo | Janice Cobb | Janice Cobb | N/A | N/A | NO | N/A | not listed in project online |  | on-going, Release driven
NISP Siebel App-RCPBS | O&M | N/A | Optimos | Lee Halbert | Joseph Adekunle | Timothy Rhodes | Dharma Reddy | Seema Dheman | Seema Dheman | N/A | N/A (COTS) | N/A | No IPT was formed | 2021-11-05 | NO | on-going, Release driven
BT-NPRC LAN | Dev | N/A | KDS | Wanda Michals | Michael Anderson | LaSheema Simmons | Garmani Maw | Janice Cobb | Janice Cobb | Yes | N/A | N/A | Not Known | 2023-08-18 | NO | This is an Infrastructure project on Prem.
Perfomance Management and Reporting System (PMRS) | O&M | PWS | ASRC Federal | Senthil Sadasivam | ThanNhi Vo | Maurice Mitchell | Alex Honch | Seema Dheman | Seema Dheman | No | Yes | No | Not Known | mm/dd/yy |  | NO CIL Report needed, Refer to descripion in the PVCS VM for thje CIL Report
Social Media Archiving Tool | Dev | N/A | N/A Innovation | Darling Richards | Falguni Jani | N/A no contract support | Carol Lagundo | Seema Dheman | Seema Dheman | No | N/A Its a SaaS project | N/A it a COTs product | N/A | mm/dd/yy
Visitor Service System (VSS) | O&M | N/A | N/A | Lee Halbert | Alexander Quiroz | Carol Harris | Ken Bostic (Acme) | Seema Dheman | Seema Dheman | No, its Release driven | N/A Its a SaaS project | N/A it a COTs product | N/A | mm/dd/yy |  | Not listed in project online
WTC_Ford Library Website Redesign | Dev | N/A | Agileana | Darling Richards | Sharmaine Anderson | James Mischke | James Mischke | janice Cobb | janice Cobb | Yes | N/A. Its a COTs product |  |  | mm/dd/yy |  | Seema reviewd and provided comments on the TP
WTC_National Archives Museum Website Redesign | O&M | N/A | Agileana | Darling Richards | Brian Voorhees | James Mischke | James Mischke | Janice Cobb | Janice Cobb | Yes |  |  | Yes | mm/dd/yy
History Hub Live Chat Enhancement |  |  |  | Darling Richards | Bobby Goddard |  |  | Janice Cobb | Janice Cobb |  | N/A it's a SaaS product | There is no custom code | Yes | mm/dd/yy |  | Pam Wright is the System Owner
A2 Data Modernization |  |  |  | Wanda Michals |  |  |  | Janice Cobb | Janice Cobb |  |  |  |  | mm/dd/yy
mm/dd/yy
Upcoming Projects
Upcoming Projects | [15 empty] | Up
IPv6 Implementation | [7 empty] | TBD | TBD |  |  |  |  | 2023-05-26 | NO
Project Online (Refer to Notes) Per convo with Tamika this is part of Office 365 | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Per PRB on 03/02/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed.
Share Point (Refer to Notes)Per convo with Tamika this is part of Office 365 | [7 empty] | Seema Dheman | Seema Dheman |  |  |  |  | 2023-05-09 | NO | Per PRB on 03/02/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed.
DCU Server Upgrade | O&M | [6 empty] | Janice Cobb | Janice Cobb |  |  |  |  | 2023-08-31 | NO | Per PRB on 03/16/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed. Email sent to LaShemma on 03/16/22.
RCPBS Upgrade | [7 empty] | TBD | TBD |  |  |  |  | 2022-04-12 | NO | Per PRB on 03/16/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed. Email sent to LaShemma on 03/16/22.
Trump Library Enhancements Updates |  |  |  |  | Brian Voorhees |  |  | TBD | TBD |  |  |  |  | mm/dd/yy |  | First email sent on 07/27/22 and 2nd email sent on 08/03/22 7/25/23 - Not in Project Online.
NARA EEO Tracking System | Dev | N/A |  | Joseph Gryder | Kenyetta Haywood | Maurice Mitchell |  | Janice Cobb | Janice Cobb | Yes | N/A its a COTS-SaaS product | No, there is no custom code | Yes | mm/dd/yy |  | IQ/Test (Chandni) wb in a monitoring role. 7/25/23 - The TP is still in draft. Seema provided comments to TP on 11/20/23
MiDAS Search and Access Portal | [7 empty] | TBD | TBD |  |  |  |  | mm/dd/yy |  | Yes
Agency and Related Services/ERA 2.0 |  |  |  |  | Jessica Bland |  |  | Seema Dheman | Seema Dheman |  |  |  |  | mm/dd/yy |  | Seema reviewed the TP and provided comments
NAC-Artificial Intelligence - Semantic Search Pilot | [7 empty] | Seema Dheman | Seema Dheman |  |  |  |  | mm/dd/yy
AAA-AISS Oracle Database upgrade |  |  |  | Senthil Kumar Sadasivam | Kenyetta Haywood |  |  | Seema Dheman | Seema Dheman |  |  |  |  | 2023-09-20 | NO | NO CM checklist or deliverables will be provided, List Refer to Email
Incorporation By Reference (IBR) | [7 empty] | Seema Dheman | Seema Dheman |  |  |  |  | mm/dd/yy |  | Sherli added to IPT on 07/11/23.Provided comments on the draft TP on 09/06/23
Artificial Intelligence Machine Learning (AI_ML) | [7 empty] | Janice Cobb | Janice Cobb
Catalog UX Improvements – Phase 2 (AAD Release 1) | Dev | [6 empty] | Seema Dheman | Seema Dheman | [6 empty] | Sherli made me the IPT member from CM side
Records Schedule & Disposition Policy Tool (RSDPT) |  |  |  | Darling Richards | Kenyetta Haywood |  |  | Janice Cobb | Janice Cobb |  |  |  | Yes | 2024-12-31 | SCHEDULED
PII Data Detection T&E | [7 empty] | Seema Dheman | Seema Dheman |  |  |  | Yes |  |  | Testing: Farooq Khan, Systems Engineering: Swapna Challa, Security: David Omorogbe.
Digital Presidential Library Portals to the Catalog | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Became part of IPT on 03/18/24
NextGen Finding Aids | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Became part of IPT on 03/18/25
Archives.gov Redesign | [7 empty] | Seema Dheman | Seema Dheman | [6 empty] | Became part of IPT on 03/18/26
Switch Upgrade - Field Sites |  |  |  | Wanda Michals | Michael Anderson/ David Orlovitz |  |  | Janice Cobb | Janice Cobb
[8 empty] | Total Count for CM Lead | Total Count for CM Analyst
[7 empty] | Seema Dheman | 23 | 23
[7 empty] | Janice Cobb | 28 | 28
[7 empty] | Total Number of Projects | 55 | 55
[7 empty] | Projects Needing CM Lead or CM Analyst | 4 | 4
Note on A54: Per Convo with TamikaTamika Ellis, Sep 1, 2021, 9:10 AM SharePoint and Project online are sort of under O365 we just put them as separate projects because they will go out after the O365 roll out. -Seema Dheman
Note on Q58: Per Richard's email Richard Steinbacher Oct 18, 2022, 2:05 PM (1 day ago) to me, Kendra Hi Seema, We will definitely provide this to you after it's finalized. Thank you, Richard On Tue, Oct 18, 2022 at 1:23 PM Seema Dheman <seema.dheman@nara.gov> wrote: Hi Richard, Please let me know whenever the TP is finalized so I can go over the CM checklist with you. Thanks On Wed, Oct 5, 2022 at 2:39 PM Richard Steinbacher <richard.steinbacher@nara.gov> wrote: Thank you Seema! -Seema Dheman

## Completed FY 24
Project Names | O&M/Dev | TDL Number/Project | Vendor | Program Manager | Project Manager/Application Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT | Deployment Date | Notes | Color Keys
OGIS Case Management System- Release II | Dev | N/A | N/A- Inhouse development | LaShemma Simmons | Jessica Bland for Rel 1 Kenyetta Haywood for Rel 2 | N/A no contract support | Suguna Vellore | Seema Dheman | Seema Dheman | Yes | N/A (COTS) | Under Development | Not Known | Release 1- 10/15/22 Releae 2- 03/07/23 | CIL Closed for Release I on 10/24/22, CIL closed for release II on 09/27/23 | Yellow- outstanding items
NISP-CMRS eVetRecs Adaptive Development | Dev | N/a | Mutatio | Lee Halbert | Baotram (BT) Le | Timothy Rhodes | Kaushal Parikh | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A |  | Closed on 12/20/23
NISP- CMRS Robotic Processing | Dev | N/A | Fearless | LaShemma Simmons | Sharmaine Anderson | Timothy Rhodes |  | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A | mm/dd/yy | Closed on 12/22/23
WTC-Carter Library Website Design | Dev | N/A | Agileana | Darling Richards | Brian Voorhees | James Mischke | James Mischke | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | N/A | N/A | 2023-07-31 | Closed on 12/27/23
WTC-Obama Library Website Upgrade | Dev | N/A | Agileana | Darling Richards | Brian Voorhees | James Mischke | James Mischke | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | N/A | N/A | 2023-07-31 | Closed on 12/27/23
COTS- Event Management System | Dev | Project | Accruent. | Jessica Martin | Joseph Adekunle | Joseph Adekunle | N/A | Seema Dheman | Seema Dheman | Yes | N/A | No, its a COTs product | Yes | 2023-02-01 | Closed on 02/29/24
BT-NARA Infrastructure | O&M | N/A | Koniag Data Solutions (KDS) | Wanda Michals | N/A | David Talon | Rick Lopez | Janice Cobb | Janice Cobb | Yes | N/A | N/A | No | N/A Release Driven | Closed on 02/23/24
COTS-Maintenance Pro Software Installation | Dev | Project | N/A COTS product | Lee Halbert | Falguni Jani | N/A | Eric Chaskes | Seema Dheman | Seema Dheman | Yes | N/A COTS product | NO | N/A | 2023-09-11
CMRS-Azure Migration | Dev | TO | Mutatio | Lee Halbert | Baotram (BT) Le | Timothy Rhodes | Robert Bibsby | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A |  | Closed on 04/08/24

## Completed FY 23
Project Names | O&M/Dev | TDL Number/Project | Vendor | Program Manager | Project Manager/Application Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT | Deployment Date | Notes | Color Keys
NISP- CMRS Digital Delivery Redesign | Dev | N/A | Mutatio | LaShemma Simmons | Joseph Adekunle | Timothy Rhodes | Joseph Adekunle | Seema Dheman | Mike Punch | Yes | Yes | Under Development | Not Known | 2022-11-17 | Closed on 02/15/23 | Yellow- outstanding items
CENSUS 2020 | Dev | N/A | No Vendor | David Lake | Falguni Jani | N/A its in house | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | No | Data Migration Project | No IPT was formed | mm/dd/yy | Closed on 05/17/23
Cloud Initiatives-ECMT | Dev | N/A |  | Darling Richards | Jessica Bland | Kevin Phelan | TBD | Janice Cobb | Janice Cobb | Yes | N/A its a SaaS product | N/A its a SaaS product | N/A | 2023-01-04 | Closed on 2/7/23
Cloud Initiatives-History Hub O&M Replacement (Modernization) | O&M | N/A | Reingold | Darling Richards | Kendra Guzman | Kendra Guzman | Jim Mischke | Janice Cobb | Janice Cobb | Yes | N/A Its a SaaS project | N/A it a COTs product | N/A | 2023-02-28 | Closed on 9/21/23
ERA POST-AAD Lift and Shift | O&M | N/A | IBM | David Lake | Jessica Bland | Frank Samuels | Michael Haines | Janice Cobb | Janice Cobb | Yes | No | Yes | N/A | 2023-07-14 | Closed on 8/29/23
ERA 2.0 Base Migration- Phase II | Dev | N/A | Enquizit | David Lake | Jessica Bland | Maurice Mitchell | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A | 2023-01-21 | Closed on 07/06/23
BT-Secure Auth PIV Implementation | Infrastruture-Dev | N/A | Secure Auth | Wanda Michals | Bobby Goddard | Brian Connor | Not Assigned | Seema Dheman | Seema Dheman | Yes | N/A (COTS) | Under Development | Not Known | mm/dd/yy | CIL Closed As Is on 07/25/23
NISP CMRS-VA Scanned Records Intake & Processing - Release II | Dev | N/A | Mutatio | Carol Harris | Baotram (BT) Le | Timothy Rhodes | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A | 2023-01-30 | Closed on 08/07/23
OGIS Case Management System- Release II | Dev | N/A | N/A- Inhouse development | LaShemma Simmons | Jessica Bland for Rel 1 Kenyetta Haywood for Rel 2 | N/A no contract support | Suguna Vellore | Seema Dheman | Seema Dheman | Yes | N/A (COTS) | Under Development | Not Known | Release 1- 10/15/22 Releae 2- 03/07/23 | CIL Closed for Release I on 10/24/22, CIL closed for release II on 09/27/23
NISP-CMRS eVetRecs Adaptive Development | Dev | N/a | Mutatio | Lee Halbert | Baotram (BT) Le | Timothy Rhodes | Kaushal Parikh | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A |  | Closed on 12/20/23
NISP- CMRS Robotic Processing | Dev | N/A | Fearless | LaShemma Simmons | Sharmaine Anderson | Timothy Rhodes |  | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A | mm/dd/yy | Closed on 12/22/23
WTC-Carter Library Website Design | Dev | N/A | Agileana | Darling Richards | Brian Voorhees | James Mischke | James Mischke | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | N/A | N/A | 2023-07-31 | Closed on 12/27/23
WTC-Obama Library Website Upgrade | Dev | N/A | Agileana | Darling Richards | Brian Voorhees | James Mischke | James Mischke | Janice Cobb | Janice Cobb | Yes | N/A. Its a COTs product | N/A | N/A | 2023-07-31 | Closed on 12/27/23
Emulated Archives social Media update |  |  |  |  | Brian Voorhees | [9 empty] | First email sent on 07/27/22 and 2nd email sent on 08/03/22. No project support was requested
Project Online (Refer to Notes) Per convo with Tamika this is patrt of Office 365 | [7 empty] | Seema Dheman | [6 empty] | Per PRB on 03/02/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed.
Share Point (Refer to Notes)Per convo with Tamika this is patrt of Office 365 | [7 empty] | Seema Dheman | [6 empty] | Per PRB on 03/02/22 Only deliverbles will be provided. NO CM Checklist or CMP is developed.
Science Logic (Canceled) | Dev | N/A | Sirius Federal | Wanda Michals | Jessica Bland | David Talon | Tony Proctor | Janice Cobb | Janice Cobb | Yes | N/A (COTS) | N/A (COTS) | Not Known | CANCELED | The product did not meet security standards. Final CIL on 07/31/23

## Completed FY 22
Project name | O&M | TDL Number | Vendor | Program Manager | Project Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT Lead | Deployment Date | Notes
Distance Learning and Collaboration Technology (Zoom) |  | N/A | None | Lee Halbert | Tamika Ellis | No COR is assginged | None | Seema Dheman | Seema Dheman | Yes | N/A its a COTS product | N/ Its a COTS product | None |  | CIL CLosed on 10/25/21
NISP Siebel App-ARCIS adaptive development |  | N/A | Optimos | Carol Harris | Timothy Rhodes | Timothy Rhodes | Raja Nannapeni | Seema Dheman | Seema Dheman | N/A | Yes | Yes | No IPT was formed |  | Closed as is on 04/14/22
EOP 40,41,42 (PERL) |  |  | Sapient | Lee Halbert | Robert Goddard | William Wingood | Kevin Liu | Seema dheman | Seema Dheman | Yes | Yes | Yes | N/A |  | CIL closed on 04/20/22
Mircrfische | No | N/A |  | Dorothy Fields | Baotram Le | Jason Hardy | None | Seema Dheman | Seema Dheman | Yes | N/A it's a COTs product | N/A | None |  | CIL completed on 05/09/22
BT- MS Identity Mgt (MIM) |  | N/A | Y-TECH | Darling Richards | Falguni Jani | David Talon | Brian Connor | Seema Dheman | Seema Dheman | Yes | No | No | PM |  | CIL Closed on 05/17/22
EOP 45-eDiscovery |  | N/A | Relativity | Tripp Duke | Kenneth Morrison | Kenneth Morrison | Yuhong Liu | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A |  | CIL CLosed on 05/17/22
History Hub (Cloud Initiative) |  | N/A |  |  | Brian Voorhees |  |  | Janice Cobb | Janice Cobb | Yes | N/A it's a SaaS product | N/A it's a SaaS product |  |  | 3/15/22 - Completed CIL 3/15/22 - Sent CM Checklist to PM 3/21/22 - Received no response from PM about the CM Checklist so I scheduled meeting with PM for 3/22/22
Cloud Initiatives-1950 Census |  | N/A | N/A Innovation | Darling Richards | Richard Steinbacher | N/A because no Vendor is invovled | Michael Knight from innovations | Seema Dheman | Seema Dheman | Yes | N/A it a COTs product | N/A it a COTs product | N/A |  | Closed on 05/03/22
NISP Siebel CMRS-In Stack Scanning |  | N/A | Mutatio | Carol Harris | Baotram (BT) Le | LaShemma Simmons | Kevin Liu | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A |  | Closed on 05/03/22
NISP CMRS-VA Scanned Records Intake & Processing - Release I |  | N/A | Mutatio | Carol Harris | Baotram (BT) Le | LaSheema Simmons | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A |  | Closed on 05/24/22
Bt/Y-Tech/SCCM |  | N/A | Y-TECH | Darling Richards | Robert Goddard | David Talon | TBD | Janice Cobb | Janice Cobb | Yes | No | NO | PM |  | CIL completed on 7/13/22
EOP-Lift and Shift |  | N/A | Sapient | Lee Halbert | Ken Morrison | William Wingood | Kevin Liu | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A | 2022-11-03 | CIL Report closed on 07/22/22
e-PACS at LBJ Library (George Bush)Refer to note |  | N/A | Stanley | Wanda Michals | Jeff Monroe | Jim Morton | Theodore Dryer | Dara Baker | Mike Punch | Yes | No | COTs product hence no Code is provided | N/A |  | Closed as-is
Drupal/George W. Bush Library Website Migration and Redesign |  | N/A | Innovation BPA | Darling Richards | Tamika Ellis |  | Michael L. Knight | Dara Baker | Dara Baker | Yes | N/A its a COTS product |  |  |  | CM only responsible for website migration, not redesign of website
DAS ORACLE Replacement |  | N/A | Satsyil | Darling Richards | Richard Steinbacher | Richard Steinbacher | Vinay Ahuja | Seema Dheman | Seema Dheman | Yes | Yes | Under Development |  |  | OBE,Replaced by DAS NextGen
Performace Measurement and Reporting System (PMRS) |  | N/A | Red River | Carol Harris | Kevin Phelan | Kevin Phelan | Mark Conrad | Seema Dheman | Seema Dheman | Yes | N/A | N/A COTs Product | Working on it |  | Moved to O&M group. CIL Closed AS IS
MDM Laptop Device Implementation |  |  |  | Wanda Michals | Falguni Jani |  | Hung Nguyen | Seema Dheman | Mike Punch | [5 empty] | Cancelled
NISP Siebel App-CMRS Adaptive |  | N/A | Optimos | Carol Harris | Baotram (BT) Le | Timothy Rhodes | Chinni Vallabhapurapu | Seema Dheman | Mike Punch | N/A | Yes | Yes | No IPT was formed |  | Closed as Is
EIS | N/A | N/A | N/A | N/A | Bobby Goddard | N/A | N/A | Seema Dheman | Seema Dheman | N/A | N/A | N/A | N/A | N/A | Comment attached
Note on P17: Per richard's email on 01/27/22 DAS ORACLE Replacement Inbox Richard Steinbacher 7:51 AM (35 minutes ago) to me Yes, please close this out. Thanks Seema. On Thu, Jan 27, 2022 at 7:44 AM Seema Dheman <seema.dheman@nara.gov> wrote: Great, Then I can remove it from the CM support list. Thanks for the quick response. On Thu, Jan 27, 2022 at 7:41 AM Richard Steinbacher <richard.steinbacher@nara.gov> wrote: Hi Seema, This project is actually OBE as it is part of the NextGen DAS project. Thank you, Richard On Thu, Jan 27, 2022 at 7:32 AM Seema Dheman <seema.dheman@nara.gov> wrote: Hi Richard, Per our earlier conversation this project is on Hold. Please let me know if the management decides to restart this project. I will not follow up on this one now. Thanks -Seema Dheman

## Completed FY 20
Project Name | TDL Number | Vendor | Program Manager | Project Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT Lead | Notes
Drupal-NARA@work | N/A | N/A- In-house development | Darling Richards | Falguni Jani | N/A no contract support | Michael Knight | Seema Dheman | Tina Dowdy | Yes | N/A | COTs product hence no Code is provided | No IPT was formed | Completed on 06/25/20 | /
Drupal-Nixon Library | N/A | N/A- In-house development | Darling Richards | Falguni Jani | N/A no contract support | Michael Knight | Seema Dheman | Tina Dowdy | Yes | N/A-COTS | COTs product hence no Code is provided | No IPT was formed | Completed on 06/25/20 | /
eVetRecs | N/A | IBM | Carol Harris | Baotram (BT) Le | Timothy Rhodes | Chinni Vallabhapurapu | Seema Dheman | Tina Dowdy | Yes | Yes | Under Development | No IPT was formed | CIL Completed successfully on 07/23/20
Drupal-Reagan Library | N/A | N/A- In-house development | Darlin Richards | Falguni Jani | N/A no contract support | Michael Knight | David Talon | Tina Dowdy | Yes | N/A-COTS | COTs product hence no Code is provided | No IPT was formed | CIL Completed on 07/28/20
NAC - Elastic Search- TO -008 | N/A | DSA | Darling Richards | Richard Steinbacher | Richard Steinbacher | Vinay Ahuja | Seema Dheman | Seema Dheman | Yes | Yes | Yes | No IPT was formed | CIL Closed as is on 07/30/20 becuase the TO was terminated
CCTV | N/A | Grunley | Wanda Michals | Janet Moreland | Rama Ganti | Dave Talon | David Talon | David Talon | Yes | No- COTS | Project Restarted after being onhold most of 2019. | Janet Morleand | CIL Completed 29 Sep 2020
Order Fulfillment and Accounting (known as O.F.A.S) | N/A | Acelo Solutions | Lee Halbert | Tim Rhodes | Tim Rhodes | Peter Staub | David Talon | David Talon | Yes | Yes | NO | n/a | CIL Completed 31 August
EOP-DATR | TDL-0014 | Sapient | Lee Halbert | Ken Morrison | BillWingood | Dyung Le | David Talon | Tina Dowdy | Yes | No- | No | No IPT was formed | Scripts were provided
eDOCs | N/A | CACI | Lee Halbert | Tim Rohodes | Tim Rohodes | Jim MIschke | David Talon | David Talon | Yes | Yes | Yes | No IPT was formed | Working with PM to close this out in Oct 2020

## Completed FY 21
Project Name | TDL Number | Vendor | Program Manager | Project Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code Exists in CM Repository | IPT Lead | Notes
Trump Library | N/A | N/A Innovation | Darling Richards | Falguni Jani | N/A because no Vendor is invovled | Michel Knight from Innovations | Seema Dheman | Seema Dheman | Yes | N/A it a COTs product | N/A it a COTs product |  | Completed on 02/25/21
ECRM | Call Order 1 | Capgemini | Darling Richards | Ed Graham | Frank Samuels | Ed Graham | Seema Dheman | Seema Dheman | Yes | N/A | COTs product hence no Code is provided | No IPT was formed | Closed on 03/09/21
ERA 2.0-BOM | Task Order | Sapient | David Lake | Jeff Monroe | Bill Wingood | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | No IPT was formed | Closed on 03/09/21
Web Quality Assurance and Accessiility Tool (WAQT) | N/A | N/A Innovation | Darling Richards | Falguni Jani | N/A no contract support | Sarah Araghi | Seema Dheman | Seema Dheman | Yes | N/A Its a SaaS project | N/A it a COTs product |  | CIL Closed 03/16/21
Drupal-Clinton library | N/A | N/A- In-house development | Darling Richards | Falguni Jani | N/A no contract support | Michael Knight | Seema Dheman | Seema Dheman | No | N/A | Data Migtation | No IPT was formed | CIL Closed on 03/24/21
ADIS | N/A | Grant Thornton | David Lake | Jeff Monroe | Bill Wingood | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | In Develpment | N/A | Completed on 04/14/21
ERA 2.0 Base Migration phase I | N/A | Sapient | David Lake | Jeff Monroe | Bill Wingood | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | N/A | Close on 04/05/21
SoftPhones | N/A | Y-TECh | Darling Richards | Robert Goddard | Same as NITTSS | Jason Hard | Seema Dheman | Seema Dheman | Yes | No | No | PM | Closed on 08/31/21
NISP Siebel CMRS-eVetREcs Field Update | N/A | Mutatio | Carol Harris | Baotram (BT) Le | LaShemma Simmons | Chinni Vallabhapurapu | Seema Dheman | Seema Dheman | Yes | Yes | Under Development |  | Closed on 08/24/21
Softphones | N/A | N/A | N/A | Robert Goddard | N/A | N/A | Seema Dheman | Seema Dheman | Yes | Yes | N/Ait a COTs pr oduct | PM | Closed on 08/31/21
Drupal- Trump Library | N/A | N/A | Darling Richards | Falguni Jani | Falguni Jani | Michael Knight | Seema Dheman | Seema Dheman | Yes | N/A | N/Ait a COTs pr oduct | N/A | Closed on 10/07/21
Office 365 | N/A | YTech | Darling Richards | Falguni Jani | N/A because no Vendor is invovled | Joe Falcione | Seema Dheman | Seema Dheman | Yes | N/A its COT product hosted in Cloud | N/ Its a COTS product |  | CIL Closed on 11/30/21
MCMD-eMuseum Public Access | N/A | Gallery Systems | Lee Halbert | Kevin Phelan | Kim Koons | David Cummings | Dara Baker | Tina Dowdy | Yes | No | N/A | Kevin Phelan | Per Tamika's email on 10/07/21NO CM Support required. Email checked in CM Repository
MCMD-reDiscovery | N/A | Gallery Systems | Lee Halbert | Kevin Phelan | Kim Koons | David Cummings | Dara Baker | Tina Dowdy | Yes | No | N/A | Kevin Phelan | Per Tamika's email on 10/07/21- NO CM Support required. Email checked in CM Repository

## Completed FY 19
Project Name | TDL Number | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Code exists in CM | IPT Lead | Notes
NISP-BIRLS |  | IBM | Jeff Monroe | Tamika Ellis | Janet Moreland | David Talon | Tina Dowdy | Yes | No | No IPT was formed |  |  | CIL Closed on 02/05/19
External Schedule Review Tool |  | Awating Vendor Selection | Darling Richards | Falguni Jani | N/A | David Talon | Tina Dowdy | Yes | N/A (COTS) | Faguni Jani |  |  | Project Cancelled.
PACS |  | Optimos | Dorothy Fields | Tamika Ellis | Tim Rhodes | David Talon | Tina Dowdy | Yes | Yes | Delray Wylie |  |  | Completed
OCAR-II |  | Optimos | Dorothy Fields | Tamika Ellis | Tim Rhodes | David Talon | Tina Dowdy | Yes | Yes | Tamika Ellis |  |  | Completed
Nara Infrastructure-Managed Print Services (MPS) |  | Optimos | Dorothy Fields | Amanda Phillips/Tamika Ellis | Tim Rhodes | David Talon | Tina Dowdy | Yes | Yes | N/A |  |  | This was cancelled as per COR email 03/07/19
NISP-CMRS 1 $2 | N/A | VION | Jeff Monroe | Tamika Ellis | Jeff Monroe | Seema Dheman | Seema Dheman | Yes | Yes | N/A |  |  | Completed on 12/14/18
NISP-CMRS-Mini Registries | TDL_06_17_TEC_0031 | IBM | David Lake | Carol Harris | Mike Haines | Seema Dheman | Seema Dheman | Yes | Yes | N/A |  |  | Production Release, Completed on 03/26/19
NISP-Special Projects |  | Ira Harley | Janet Moreland | Janet Moreland | Janet Moreland | Seema Dheman | Seema Dheman | Yes | N/A(SaaS) | No IPT was formed |  |  | Completed on 03/26/19
NISP-QA Module |  | Maximo | Dorothy Fields | Tamika Ellis | Tim Rhodes | Seema Dheman | Seema Dheman | Yes | Yes | No IPT was formed |  |  | Completed on 03/26/19
Drupal- Museum Website |  | N/A- In-house development |  | Falguni Jani | N/A no contract support | Seema Dheman | Tina Dowdy | Yes | Yes | No IPT was formed |  |  | Completed on 2/8/19
ERA 2.0 |  | Attain | Wanda Michals | N/A | Rick Lopez | Seema Dheman | Seema Dheman | Yes | N/A Doc only | No IPT was formed |  |  | Completed on 04/04/19
Classified Interim System (CIS) | TDL -16 | SAIC | Mark Busby | Marjorie Bennett | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes | N/A- documents only | No IPT was formed |  |  | CIL Closed on 04/12/19
eSAN - Phase 2 | Not Known | Not Known | Dorothy Fields | Joe Falcione | Do not know yet | Seema Dheman | Seema Dheman | Do not know | N/A | No IPT was formed |  |  | Per Seema's email on 04/26/19 this project is closed and CM team did not get any documentation E-SAN Phase I and II Inbox x Seema Dheman <seema.dheman@nara.gov> Fri, Apr 26, 9:33 AM (3 days ago) to Joe, Edward, me Gentlemen, Just wanted to let you know that this project was to refresh the NISP Hardware(eSAN Phase-2) to remedy the situation with migrating the ARCIS, CMRS and HMS implementations to new hardware which was replacing the Solaris servers from Development, QA and Production environments with newly purchased Oracle Hardware. In my opinion it was part of the Tech Refresh activity. CM did not get any documents for this project. I am closing this project from CM perspective unless you disagree. Thanks and enjoy the weekend.
VSS | N/A |  |  | Falguni Jani | Carol Harris | Seema Dheman | Seema Dheman | Yes | N/A (COTS) | No IPT was formed |  |  | CIL closed on 05/21/19
DAS Stablization | Task order 6 | DSA | Jesse Alexander | Janet Moreland | Richard Steinbacher | Seema Dheman | Seema Dheman | Yes | Yes | N/A |  |  | CIL closed on 06/25/19
Catalog-NAC | Task Order 7 | DSA | Darling Richards | Richard Steibacher | Richard Steibacher | Gulam Shakir | Seema Dheman | Seema Dheman | Yes | Yes | Yes | N/A | CIL_CLosed_08/29/19
ERA 2.0-Fix Pack 1 | Task Order | SAIC | David Lake | Jeff Monroe | Bill Wingood | Kevin McCarthy | Seema Dheman | Seema Dheman | Yes | Yes | Under Development | No IPT was formed | CIL_Closed_09/24/19
Catalog-NAC | Task Order 4 | DSA | Darling Richards | Richard Steibacher | Richard Steibacher | Gulam Shakir | Seema Dheman | Seema Dheman | Yes | Yes | Yes | N/A | CIL_Closed_10/28/19
WEB BPA API Design | RFQ-006 | IBM | Carol Harris | Falguni Jani | Timothy Rhodes | Larry Tabacon | Seema Dheman | Seema Dheman | Yes | N/A Documentation Only | N/A | No IPT was formed | CIL_Closed_11/07/19
Catalog- TO 008 | Task Order | DSA | Darling Richards | Richard Steinbacher | Richard Steinbacher | Vinay Ahuja | Seema Dheman | Seema Dheman | Yes | Yes | Not yet | N/A | This is closed becuase it will part of the EPAC project

## Completed FY 18
Project Name | TDL Number | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Notes
EA-ERA Annual Move | TDL-17 | SAIC | Mark Busby | Marjorie Bennett | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes | N/A- documents only | N/A | Completed on 03/23/18
EA-ADRRES and URTS System Evolution Plans | TDL-19 | SAIC | Mark Busby | Marjorie Bennett | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes | N/A- documents only | N/A | Completed on 03/23/19
DAS/ERA 2.0 Analysis and Assessment (AA) | TDL_06_17_TEC_0030 | IBM | Jesse Alexander | Richard Steinbacher | Mike Haines | Janice Cobb | Janice Cobb | Yes | Documentation Only | N/A | Completed 2/15/18
EOP -44 | Task Order 005 | IBM | Jesse Alexander | Richard Steinbacher | Mike Haines | Seema Dheman | Seema Dheman | Yes | Documentation Only | N/A | Completed on 02/14/18
Active Directory |  | Attain | Wanda Michals | N/A | Rick Lopez | Janice Cobb | Janice Cobb | Yes | N/A | No | Completed (Phase 1)
NISP-Adaptive Development | N/A | Optimos | Dorothy Fields | Tamika Ellis | Tim Rhodes | Seema Dheman | Seema Dheman | Yes | Yes | Seema Dheman | Completed on 01/26/18
eCASE-SW/HW Request Form Use case | N/A | Tegance | Darlene Richards | Vera Williams | Joe Falcione | Seema Dheman | Seema Dheman | Yes | N/A-SAAS | Vera Williams | Stopped by the SLT
Learning Management System (LMS) |  | cornerstone OnDemand | Ira Harley | LaShemma Simmons | Steven Flowers | Seema Dheman | Seema Dheman | Yes | N/A (COTS) | Seema Dheman | CIL Closed on 05/25/18
EA SDLC | TDL-18 | SAIC | Mark Busby | Marjorie Bennett | Marjorie Bennett | David Talon | David Talon | Yes | N/A- documents only | N/A | CIL Closed 06/01/18
EA SDLC (2nd TDL) | TDL-22 | SAIC | David Lake | Carol Harris | Marjorie Bennett | David Talon | David Talon | Yes | No | No IPT was formed | CIL Closed 06/07/18
EA SDLC | TDl-21 | SAIC | Mark Busby | Dyung Le | Marjorie Bennett | David Talon | David Talon | Yes | N/A- documents only | N/A | CIL Closed on 06/01/18
EA-Systems Evolution Plans |  | IBM | David Lake | Carol Harris | Mike Haines | David Talon | David Talon | Yes | Yes |  | Per meeting with David on 07/26/18 this project is closed
ERA Business Processing Reengineering (BPR) | N/A | Attain | Wanda Michals | Carol Harris | Rick Lopez | David Talon | David Talon | Yes | N/A |  | Per meeting with David on 07/26/18 this project is closed Documentation Only
History Hub/ICN |  | Optimos | Dorothy Fields | Tamika Ellis | Tim Rhodes | David Talon | David Talon | Yes | Yes | Dave Talon | Per meeting with David on 07/26/18 this project is closed
NARA Sharedrive Plan | N/A | Caliber Systems | Jesse Alexander | Delray Wylie | Janet Moreland | David Talon | David Talon | Yes | N/A (COTS) | No IPT was formed | Per meeting with David on 07/26/18 this project is closed
NISP-Training |  | N/A | Dorothy Fields | BT | BT | David Talon | David Talon | Yes | N/A (COTS) | No IPT was formed | Per meeting with Dave Talon on 07/26/18 this project is cancelled
Microfiche |  |  |  | Janet Moreland |  | Seema Dheman | Seema Dheman | Yes
HMS-Presidential Library |  | Maximo | Dorothy Fields | BT | Tim Rhodes | Seema Dheman | Seema Dheman | Yes | Yes | Do not know | Completed on 10/23/18
EOP 44 Assessment (Obama Transition) |  | Reingold | Ira Harley | LaShemma Simmons | Steven Flowers | Seema Dheman | Seema Dheman | Yes |  | No IPT was formed | Completed on 11/30/18
Share Drive |  | NA | Delray Wylie | Delray Wylie | N/A | David Talon | Tina Dowdy | No | No | Mike Haines | This is an inhouse project to "cleanup" the Share drives and was transformed into Google team Drive
NISP-eVetRecs |  | Maximo | Dorothy Fields | Tamika Ellis | Tim Rhodes | Seema Dheman | Seema Dheman | Yes | Yes | No IPT was formed | CIL Closed on 12/21/18
Electronic Performance Mgt System (ePMS) | [5 empty] | Dave Talon | Tina Dowdy |  |  |  | Project cancelled by CIO in June 2017
Maximo | Project | Maximus | Ira Harley | Janet Moreland | Tim Rhodes | Seema Dheman | Tina Dowdy | Yes | No | No | Maxmimo is closed and is with BX. No CM support is requested from CM Team
Note on L21: Per Sam Lee email on 12/03/18 Clean up share drive Inbox x Samuel Lee 12:52 PM (2 minutes ago) to me, David Yes, I agree. Thanks. On Mon, Dec 3, 2018 at 12:44 PM Seema Dheman <seema.dheman@nara.gov> wrote: Sam, Since its transformed it into Google Team Drive now so from CM perspective its closed. Please let me know if you disagree. thanks On Mon, Dec 3, 2018 at 12:39 PM Samuel Lee <Samuel.Lee@nara.gov> wrote: I think this effort morphed into the Share Drive Migration. The original plan was to migrate files into Microsoft shares, but the target is Google Team drive now. Thanks. On Mon, Dec 3, 2018 at 10:47 AM Seema Dheman <seema.dheman@nara.gov> wrote: Hi Sam, Is the Clean up share Drive project completed? Please let me know. Thanks -Seema Dheman

## Completed FY 17
TDL Number | Project Name | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Notes
| Automated Disposition Authority Processing Tool (ADAPT) |  |  | Billie Williams-Henderson | Billie Williams-Henderson | Janice Cobb | Janice Cobb | No | Yes |  | As of 5/15/17, this project is being decommissioned.
N/A | Clarity |  |  | Billie Williams-Henderson | Scott Birckhead | Seema Dheman | Seema Dheman | Yes | N/A- COTS Product |  | Clarity is replacement for PROMT. It’s a COTs product and a cloud based service (SaaS). All the documents are checked into CM Repository
| CRI |  |  | Tamika Ellis |  | Seema Dheman | Dean Hansen | Yes |  | N/A
TDL 0014 | EA-EOP OBAMA Asssesment | SAIC | None | Dyung Le | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes |  |  | \
TDL_0013 | Enterprise Architecture | SAIC | None | Dyung Le | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes |  |  | Completed
TDL_05_17_EOP_0028 | ERA A2 Infrastructure | IBM |  | Jeremy Yates | Amy Anderson/Mike Haines | Seema Dheman | Seema Dheman | Yes | HW changes only, CMDB was submitted no Source code requied |  | Completed
TDL_0012 | Enterprise Architecture | SAIC | None | Dyung Le | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes | N/A- Documentation Only |  | Completed
TDL_05_17_TEC_0029 | ERA Base Non-Production Lab Transition | IBM | David Lake | David Lake | Amy Anderson | Seema Dheman | Dean Hansen |  |  |  | Completed
| LACS |  |  | Tamika Ellis | Sandra Paul-Blanc | Janice Cobb | Elena Donskaia | Yes |  |  | The project close date is 04/29/16.
| Mobile Device upgrade | N/A |  | Billie Henderson | Amy Anderson | Seema Dheman | Seema Dheman | N/A |  |  | No CM support required. Email in PVCS under Enterprise CM folder
TDL 0015 | NAC Assessment | SAIC |  | Sam Le | Sam Lee | Seema Dheman | Elena Donskaia | Yes |  | N/A | Completed
N/A | SEIP Ingest Process | ViON | Ken Hawkins | Carol Harris |  | Seema Dheman | Elena Donskaia | Yes |  |  | Completed
| Website Digital Design & Development (DDDS)- Obama Library |  |  |  |  | Seema Dheman | Seema Dheman | Yes | N/A- its website hosting using COTS product | Seema Dheman | Completed
| EOP 43 | VION | Jeff Monroe | Tamika Ellis | Jeff Monroe | Seema Dheman | Seema Dheman | Yes | Yes | N/A
| Network Modernization | Tim Rhodes | Tim Rhodes | Tim Rhodes |  | Seema Dheman | Seema Dheman | Yes | N/A (COTS) | No IPT was formed | Completed
ERA 2.0/DOR | TDL-26 | IBM | David Lake | Carol Harris | Mike Haines | Janice Cobb | Janice Cobb | Yes | Yes |  | Completed
ERA 2.0/DPE | TDL-27 | IBM | David Lake | Carol Harris | Mike Haines | Janice Cobb | Janice Cobb | Yes | Yes |  | Completed

## Completed FY16
TDL Number | Project Name | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | IPT Lead | Notes
TDL_02_14_TEC_0012 | Part III of Migration and Implementation Plan | IBM | N/A | Amanda Phillips |  | Seema Dheman | Elena Donskaia
TDL_02_14_TEC_0015 | ERA 2.0/BOM | IBM | David Lake | Tony Paul | Amy Anderson | Janice Cobb | Elena Donskaia | Yes |  | Note: submitted a reminder to PM for the TDL to apply to the Data Dictionary GFI on 2/25/16.
| Ford Museum Learning Center |  | Bill D. | Bill Day |  | Elena Donskaia |  | TBD |  | Per the IT Projects List dated 2/3/16, this is a potential Operations project.
| Remedy on Premise |  |  |  |  | Seema Dheman | Seema Dheman | Yes |  | Completed
N/A | Remote Access System Upgrade (Citrix Upgrade |  |  | Amanda Phillips |  | Seema Dheman | Seema Dheman | Yes |  | Completed on 05/16/16
| Rediscovery to MCMD |  |  | Kim Koons |  | LaShemma Simmons | Elena Donskaia | Elena Donskaia | N/A | CM support is not required. It involes migration of all Rediscovery users into MCMD system. So no HW or SW changes just moving users from TMS to MCMD
N/A | Remedy Force Implementation | IBM |  | Judy Weight | Amy Anderson | Seema Dheman | Seema Dheman | Yes |  | The project was closed on 02/23/16 and the Project close out Note was checked into CM Library.
TDL 0014 | Enterprise Architecture(EOP Assessment) | SAIC | None | Dyung Le | Marjorie Bennett | Seema Dheman | Seema Dheman | Yes |  | Completed on 06/03/16
N/A | IPV6 |  |  |  |  | Seema Dheman | Seema Dheman | Yes |  | Completed on 08/11/15
TDL_03_15_TEC_0016_Web_Methods | BASE Software Corrective Maintenance for webMethods | TBD | TBD | TBD | Amy Anderson | Seema Dheman | Seema Dheman | Yes |  | Completed
| Security Clearance Tracking System (SCTS) | Micropat |  |  |  | Seema Dheman | Seema Dheman | N/A |  | SaaS application. No support was asked from PM
N/A | CuadraStar Technical Refresh Project |  | Ira Harley | Tamika Ellis | Ira Harley | Seema Dheman | Seema Dheman | Yes | N/A | Per Penny's email on 12/17/14:Phuong Ha 1:26 PM (13 minutes ago) to Carol, Daniel, David, Janice, Kimberly, Sara, me, Tuong-Vi, William Heads-up on new project!Meeting scheduled for 01/29/15 Per conversation with Tom M on 01/28/15 Ira is the lead for this project. CIL Completed on 12/04/15
Total Number of Projects Closed in FY16:
10

## CM Only Activities
Activity | IQC Lead | IQC Alternate | Start | Finish | Status | Notes | In PVCS
Projects
CM Repository- Physical library- Source code and documention if needed | Dave Talon | Tina dowdy |  |  |  | Andrew will maintain the library
PLANS | [7 empty] | In-Progress
Update the ERA CMP | Janice/Seema | [6 empty] | Not Started
Update the ERA Audit Plan | Dave Talon |  |  |  |  | Revisit |  | Completed
SOPS
How to conduct an FCA/PCA Audit | Dave/Andrew
Create a Production Baseline | Dean Hansen | Seema Dheman | Update Started 10/19/16 | Previous Completion 8/29/2014 | In-Progress
ERA Naming and Labeling Conventions | CM Team | CM Team |  |  | Completed |  | Yes
Project Initiation Process (Revisions) | Dave/Andrew |  | 2014-07-11 | 2014-07-31 | Completed |  | Yes
Project Close-out
CM Artifacts (templates, forms, and checklists)
ECCB RFC Form | Seema Dheman/Janice Cobb | [5 empty] | Yes
Version Description Document (VDD) | [5 empty] | Check version in PVCS
CMP Template | CM Team | CM Team |  |  | In-Progress
CM Reports
Creation and maintenance of CIL reports for new and existing projects | CM Team | CM Team |  |  | On-Going
CM Training
CM Process Training | CM Team | CM Team

## On_Hold Status
TDL Number | Project Name | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Notes
| Researcher Registration System (RRS) |  | Ira H. |  |  | Seema Dheman | Seema Dheman |  |  |  | Per Ira's email on 09/09/15-RRS is on hold status on this time since source selection was cancelled. (ip)
| e-VETS RECS 2.0 |  | Joe |  |  | Seema Dheman | Seema Dheman |  |  |  | Project on hold. It will subsumed by CMRS. NO CM suppot required at this time Email sent to Joe Falcione on 04/22/16 (ip)
| Audits and Assurance II-P | N/A | Deborah Steel | Mamta Rai |  | Seema Dheman | Seema Dheman | N/A | N/A |  | Documentation only. On Hold
| CCTV |  | Wanda Michals | Delray Wiley |  | David Talon | David Talon | Yes | N/A | N/A | Per IPJ-RPRT-Project_Status ...Awatiting Funding, On Hold
| Document Utility Conversion (DCU) |  |  | Delray Wiley |  | David Talon | David Talon | No |  | N/A | David became CM Lead starting Jan 6, 2017. Per the IPJ-RPRT-Project_Status-20170530 its in deferred status
| ePMS |  |  | Kevin Phelan |  | David Talon | David Talon |  |  | David Talon | Per IPJ-RPRT-Project on 05/30/17_Status ...Awatiting Funding, On Hold.
Digitization Lab Hitachi SAN Replacement |  | Not known at this time | Wanda Michals | Kevin Phelan | Do not know yet | Seema Dheman | Seema Dheman | Yes |  |  | Project on hold for pending the sign-off of a NARA-approved baseline for Windows Server 2016
Virtulization Project | [10 empty] | Samuel Lee 10:27 AM (29 minutes ago) to Thomas, me I do not recall this project, either. No PM assignment is available. On Mon, May 20, 2019 at 9:44 AM Thomas Mcandrew <Thomas.McAndrew@nara.gov> wrote: Seema, I am not familiar with this project? Is this an Ops project? Thanks, Tom M
| SCTS Security Clearance Tracking | MicroPact | Ira Harley | Deb Anderson | Jeff Monroe | David Talon | David Talon | Yes | No | no ipt | This has been extened one year to allow for a new PWS- 0n hold
Total Number of Closed Projects:
7

## References
•Technology Refresh: IT Investments that consist of a hardware or software technology refresh that do not significantly change existing business processes. The minimum dollar threshold is $1 and there is no maximum dollar threshold. •Small: IT Investments with Development Modernization and Enhancement (DME) costs between $1 and $1 million (M) OR annual Operations and Maintenance (O&M) (i.e., steady state) costs between $1 and $500 thousand (K). •Medium: IT Investments with DME costs between $1M and $10M OR annual O&M (steady state) costs between $500K and $1M. •Large: IT Investments with costs of at least $10M OR annual O&M (i.e., steady state) costs of at least $1M. Financial management systems or investments that are deemed by the CIO to be mission-critical to NARA also fall into this threshold.

## CM Support not Req
Project Name | TDL Number | Vendor | Program Manager | Project Manager | COR | Technical POC | CM Lead | CM Analyst | CIL Required? | Source Code Required? | Code exists in CM | IPT Lead | Notes
Enterprise Asset Management (EAM) |  |  | Ira Harley |  |  |  | Seema Dheman | Seema Dheman | N/A |  |  |  | NO CM support is required at this time. Ira infromed informally to Seema
Case Management |  |  | Darling Richards |  | Marlon Andrews |  | Seema Dheman | Seema Dheman |  |  |  |  | CM support is not required at this time. Per Marlon's email on 06/15/17: CM Support is not required at this time since we have only acquired licenses. We are doing phase two to get an integrator and when that is awarded (September) than we will need CM.
Infrastructure A2 Cabling |  |  | Wanda Michals | Bill Day |  |  |  |  | No |  |  |  | Per conversation with Bill Day no contract support required for A2 Cabling
1940 Census Redesign |  |  |  | Falguni Jani |  |  | David Talon | David Talon |  |  |  |  | On Hold
PDMT (Jira Tool) | N/A | TBD | Darling Richards | Falguni Jani | TBD | Andrew Wilson | David Talon | David Talon | NO | No | N/A | No IPT was formed | These requirements were moved to 1950 Census.

## Completed
TDL Number | Project Name | Vendor | Program Manager | Project Manager | COR | CM Lead | CM Analyst | CIL Required? | Source Code Required? | IPT Lead | Notes
TDL_01_13_AAD_0009 | AAD Development/Test Site Implementation Plan | Deb Steel | Frank Samuels | Development | 2013-07-29 | Carol Harris | Seema Dheman
TDL_02_14_TEC_0003 | Cloud Development and Test |  |  |  | Unk | Unk | Kim Scates
TDL_00_12_TEC_0004 | Consolidate and Refresh the NetApp Infrastructure | Amy Anderson |  | Documentation | 2012-09-25 | Carol Harris | Seema Dheman
FY13-ITAS-PM-TDL-003 | Digital Processing Environment (DPE) | David Lake | Frank Samuels | Documentation | 2013-10-24 | Seema Dheman | Kim Scates
TDL _00_12_BAS_0001-1 | Download of Search Results |  |  | Development | 2012-05-11 | N/A | Seema Dheman
ITAS-PM-TDL-003 | Electronic Performance Management System | Jim Mischke | Jim Mischke | Development | 2013-10-28 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enhancement of NARA Web Filtering (EWF) | Laima Kuring | Laima Kuring | Documentation | 2013-11-26 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Asset Management(EAM) | Ira Harley | Ira Harley | Documentation | 2013-10-22 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Backup (EB) | Queenie Ogden | Queenie Ogden | Documentation | 2014-01-24 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Cloud Strategy (ECS) | Frank Samuels | Frank Samuels | Documentation | 2013-12-18 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Identity Management / HSPD-12 Concept (EIM) | William Day | William Day | Documentation | 2013-11-14 | Seema Dheman | Seema Dheman
ITAS-PM TDL-0001 | Enterprise Storage Management (ESM) | Queenie Ogden | Queenie Ogden | Documentation | 2014-01-24 | Seema Dheman | Seema Dheman
EOP Data Migration | EOP Data Migration | Ken Hawkins | Tom McAndrew | Development |  | Carol Harris
EOP Upgrade | EOP Small Tasks | Ken Hawkins | Tom McAndrew | Development |  | Carol Harris | Kim Scates
TDL_01_13_EOP_0005 | EOP Small Tasks |  |  | IBM | Ken Hawkins
TDL_02_14_BAS_0011 | ERA Base Browser Compatibility | David Lake | Frank Samuels | Development | 2013-09-27 | Carol Harris | Seema Dheman
TDL_00_12_BAS_0001-2 | ERA Base Performance Analysis | David Lake | Frank Samuels | Documentation | 2012-06-18 | N/A | Kim Scates
TDL_01_13_BAS_0001-3 | ERA Base Search Performance |  |  | IBM
TDL_00_12_TEC_0003 | ERA Development and Test in IBM Smart Cloud | Dyung Le |  | Development | 2012-09-25 | Carol Harris | Kim Scates
| FOIA Functionality | med | 1 | VION | Ken Hawkins
FY13-ITAS-PM-TDL-001 | Google Gaps |  |  | Development |  | Seema Dheman | Seema Dheman
Cellular Repeater |  | 1 | Biil D.
TDL_X.X | OCAR | med | 1
TDL_00_12_OPA_0002 | Online Public Access (OPA) Instance of ERA | Richard Steinbacher |  | Development | 2012-08-15 | Carol Harris | Kim Scates
Project ID | Project Name | Program Manager | Project Manager | Project Type | Baseline Start | CM Project Lead | CM Project Analyst
TDL_01_13_OPA_0008 | Public Access to EOP43 via OPA | Richard Steinbacher | Dorothy Fields | Development | 2013-07-15 | Carol Harris | Seema Dheman
ITAS-PM-TDL-005 | Researcher Registration |  | Ira Harley | Documentation | 2013-09-27 | Seema Dheman | Seema Dheman
Unified Communications (UC) | SAIC |  |  | Documentation | 2013-12-30 | Seema Dheman | Seema Dheman
TDL_01_13_TEC_0006 | SE Base Small Fixes | Dyung Le | Frank Samuels | Development | 2013-09-30 | Carol Harris | Seema Dheman
TDL_02_13_SEC_0010 | Security Fixes | Ben McElyea | Amy Anderson | Development | 2013-09-30 | Carol Harris | Seema Dheman
TDL_01_13_TEC_0007 | Tech Refresh part II | Amy Anderson | Amy Anderson | Development | 2013-07-23 | Carol Harris | Seema Dheman
ITAS-PM TDL-0001 | Websites to the Cloud (WTC) | Theodore Dryer | Theodore Dryer | Documentation | 2013-11-13 | Seema Dheman | Seema Dheman
| Mobile Device Management |  |  |  |  | Janice Cobb
N/A | SIP |  |  |  |  | Seema Dheman | Elena Donskaia |  |  |  | Project has been completed.
| Web Server Refresh |  |  |  |  | Seema Dheman | Seema Dheman |  |  |  | No CM support required as per IT Projects meeting on 11/19/15 (G)
N/A | Digital Signage |  | Alex Turrel | Vera Williams |  | Seema Dheman |  |  |  |  | No CM support required. Project closed. Email checked into PVCS
| Website to Cloud (WTC) | Viderity | Wanda Michals | Vera Williams | Brian Connor | Janice Cobb | Janice Cobb | No | No |  | Cloud hosting.
Total Number of Closed Projects:
35